## Sheet1
Source: https://docs.google.com/spreadsheets/d/1S_TQxYAJk89aKOq42i9al8Od_wyd2huCxCLL5ttc2zw/edit#gid=0
Component | Priority | Estimated Time | Actual Time
title animation and interactivity | H | 10hr | 2hr
Project grid and each page within | H | 10hr | 5hr for grid and 25hr for sub-project 1 and 2
Navbar | H | 3hr | 24hr
Body, and photo | H | 3hr | 3hr
Social Media Icons in footer | L | 1hr | 3hr
Total | H | 27hr | 62 hrs
Day | Deliverable | Status
Day 1 | Project Description | Complete
Day 2-3 | HTML, CSS | Complete
Day 3 | JS for navbar and grid and html/css for each page within grid | Complete
Day 4 | title animation and interactivity | Complete
Day 5 | finishing touches | Complete
Day 6 | Present | Complete